## Unit Testing
Project Name: |  | GO MOMMY!
Created by: |  | Sunshine Richmer Palahang
Date of creation: |  | 2023-06-13
Date of review:
TEST CASE ID | TEST SCENARIO | TEST CASE | PRE-CONDITION | TEST STEPS | TEST DATA | EXPECTED RESULT | POST CONDITION | ACTUAL RESULT | STATUS (PASS/FAIL) | Code by: | Tested by:
UT_SPLASH_001 | Verify that when User selects app Logo Splash screen is displayed with App Logo | Launch Application | 1. Test environment setup 2. Test data preparation 3. Test Availabity | 1. open application |  | When user selects app, splash screen of app logo should be displayed | ImageView should remain for 3s only | App Logo displayed for no more than 3sec | PASS | DE VEGA & BAROTO | PALAHANG
2. show splash screen for 3sec
3. exit splash screen
UT_WELCOME_001 | Verify that when Splash screen end, welcome greetings will show | Launch Application | 1. Test environment setup 2. Test data preparation 3. Test Availabity | 1. open application |  | When splash screen is done displaying, welcome greetings should be displayed | ImageView should remain for 3s only | Welcome greetings for user displayed for no more than 3sec | PASS | DE VEGA & BAROTO | PALAHANG
2. show splash screen for 3sec
3. show welcome greetings
UT_T&C_001 | User agree on Terms and conditions | Tap gesture on checkbox | 1. User must tap checkbox | 1. Click checkbox |  | User clicked on checkbox, Checkbox button background changes | CheckBox button should appear shaded | CheckBox button background color changes | PASS | DE VEGA & BAROTO | PALAHANG
UT_AGREE_001 | User agree on Terms and conditions | Tap gesture on checkbox | 1. User must tap all checkbox | 1. Click all checkbox |  | User clicked on checkbox, next button background changes | NextButton enabled | NextButton background color changes | PASS | DE VEGA & BAROTO | PALAHANG
UT_T&CDialog_001 | User agree on Terms and conditions | Tap gesture on designated interactive text | 1. User must tap Text | 1. Click "Privacy Policy and Terms of Use" |  | User clicked on interactive text, scrollable dialog box will appear | Dialog Box | Dialog Box appears | PASS | DE VEGA & ESGUERRA | PALAHANG
UT_T&CIunderstand_001 | User agree on Terms and conditions | Tap gesture on designated interactive text | 1. User must tap Text | 1. Click "Privacy Policy and Terms of Use" |  | User clicked on interactive text, dialog box will disappear | Dialog Box | Dialog Box disappears | PASS | DE VEGA & ESGUERRA | PALAHANG
2. Click "I understand"
UT_NEXT_001 | User agree on Terms and conditions | Tap gesture on designated interactive button | 1. All checkbox are checked | 1. Click next button |  | User clicked on next button, next activity will appear | New activity will appear | Login activity appears | PASS | DE VEGA & BAROTO | PALAHANG
UT_LOGINEmail_001 | Registered user tries to login within the mobile application. | Input Email | 1. Input plain text | 1. Input Text in EditText Field |  | "Email" will be change to user input | User Input | "Email" change with user input with different text color | PASS | DE VEGA & ESGUERRA | PALAHANG
UT_LOGINPass_001 | Registered user tries to login within the mobile application. | Input Password | 1. Input plain text | 1. Input Text in EditText Field |  | "Password" will be change to user input | User Input | "Password" change with user input with different text color | PASS | DE VEGA & ESGUERRA | PALAHANG
UT_LOGINShow_001 | Registered user tries to login within the mobile application. | Show input password | 1. Password 2. Hide view 3. Toggle Button | 1. Click Toggle Button |  | Toggle Button will change and Password in plaintext view will show | Password | Shows password | PASS | DE VEGA & ESGUERRA | PALAHANG
UT_LOGINButton_001 | Registered user tries to login within the mobile application. | Enter valid User Name and valid Password | 1. Registered Email Address required. 2. Password must match from stored credentials. | 1. Enter E-mail Address | <Valid User Name> | User input required fields, login button will change change color | Login Button enabled | Login button color changes and enabled | PASS | DE VEGA & ESGUERRA | PALAHANG
|  |  |  | 2. Enter Password | <Valid Password>
UT_LOGIN_001 | Registered user tries to login within the mobile application. | Tap gesture on designated interactive button | 1. Registered Email Address required. 2. Password must match from stored credentials. | 1. Enter E-mail Address | <Valid User Name> | User clicked on login button, next activity will appear | New activity will appear | Homepage activity appears | PASS | DE VEGA & ESGUERRA | PALAHANG
|  |  |  | 2. Enter Password | <Valid Password>
3. Click "Login" button
UT_LOGIN_002 | Registered user tries to login within the mobile application. | Tap gesture on designated interactive text | 1. User do not have an account registered | 1. Click "Create Account" |  | User clicked on create account button, create account activity will appear | Create account | Create Account Activity appears | PASS | DE VEGA & ESGUERRA | PALAHANG
UT_FORGOT_001 | Registered user tries to login within the mobile application. | Tap gesture on designated interactive text | 1. Registered Email Address Required | 1. Click "Forgot Password?" |  | User clicked on forgot password interactive text, forgot password activity will appear | New activity will appear | "Forgot Password?" interactive text is unable to click | FAIL | BAROTO & ESGUERRA | PALAHANG
UT_CREATEUser_001 | New user tries to create an account within the mobile application. | Input User name | 1. Input plain text | 1. Input Text in EditText Field |  | "Username" will be change to user input | User Input | "Username" change with user input with different text color | PASS | DE VEGA & ESGUERRA | PALAHANG
UT_CREATEEmail_001 | New user tries to create an account within the mobile application. | Input Email | 1. Input plain text | 1. Input Text in EditText Field |  | "Email" will be change to user input | User Input | "Email" change with user input with different text color | PASS | DE VEGA & ESGUERRA | PALAHANG
UT_CREATEPass_001 | New user tries to create an account within the mobile application. | Input Password | 1. Input plain text | 1. Input Text in EditText Field |  | "Password" will be change to user input | User Input | "Password" change with user input with different text color | PASS | DE VEGA & ESGUERRA | PALAHANG
UT_CREATEConfirm_001 | New user tries to create an account within the mobile application. | Enter valid User Name and valid Password | 1. Email Address required. 2. Password must reach parameters. | 1. Enter E-mail Address | <Valid User Name> | User input required fields, login button will change change color | Login Button enabled | Login button color changes and enabled | PASS | DE VEGA & ESGUERRA | PALAHANG
|  |  |  | 2. Enter Password | <Valid Password>
UT_CREATEButton_001 | New user tries to create an account within the mobile application. | Tap gesture on designated interactive button | 1. Email Address required. 2. Password must reach parameters. | 1. Enter E-mail Address | <Valid User Name> | User clicked on login button, next activity will appear | New activity will appear | Mom Experience activity appears | PASS | DE VEGA & ESGUERRA | PALAHANG
|  |  |  | 2. Enter Password and Confirm Password | <Valid Password>
|  |  |  | 3. Click "Create Account" button | <Password Match>
UT_CREATEGoogle_001 | New user tries to create an account within the mobile application. | Tap gesture on designated interactive button | 1. Google Account required. | 1. Click "Create with Google " |  | User clicked on create with google button, google account/s will appear | Google Account | "Create with Google" button is unable to click | FAIL | BAROTO & ESGUERRA | PALAHANG
UT_CREATELogin_001 | Registered user tries to login within the mobile application. | Tap gesture on designated interactive text | 1. User must tap Text | 1. Click "Login" |  | User clicked on login interactive text, login activity will appear | Registered Account | Login activity appears | PASS | DE VEGA & ESGUERRA | PALAHANG
UT_MOMEXPYes_001 | New user tries to create an account within the mobile application. | Tap gesture on designated interactive button | 1. User must tap one button | 1. Click "Yes, I am a first time mom" |  | User clicked on yes button, next activity will appear | New activity will appear | Birthyear picker activity appears | PASS | DE VEGA & ESGUERRA | PALAHANG
UT_MOMEXPNo_001 | New user tries to create an account within the mobile application. | Tap gesture on designated interactive button | 1. User must tap one button | 1. Click "No, I have had children before" |  | User clicked on no button, next activity will appear | New activity will appear | Birthyear picker activity appears | PASS | DE VEGA & ESGUERRA | PALAHANG
UT_BIRTHPicker_001 | New user tries to create an account within the mobile application. | Scroll gesture on designated number picker button | 1. User must scroll the number picker | 1. Scroll number picker | <Birthyear> | User scroll number picker for birth years | Birth years | Picks birth year | PASS | DE VEGA & ESGUERRA | PALAHANG
UT_BIRTHSelect_001 | New user tries to create an account within the mobile application. | Scroll gesture on designated number picker button | 1. User must scroll the number picker | 1. Scroll number picker | <Birthyear> | User scroll number picker for birth years, Select Button will change color | Select Button enabled | Select button color changes and enabled | PASS | DE VEGA & ESGUERRA | PALAHANG
UT_BIRTHButton_001 | New user tries to create an account within the mobile application. | Tap gesture on designated interactive button | 1. User must scroll the number picker | 1. Scroll number picker | <Birthyear> | User clicked on select button, next activity will appear | New activity will appear | User Due date activity appears | PASS | DE VEGA & ESGUERRA | PALAHANG
2. Click "Select"
UT_DUEMonth_001 | New user tries to create an account within the mobile application. | Scroll gesture on designated number picker button | 1. User must scroll the number picker | 1. Scroll number picker | <Due Month> | User scroll number picker for due month | Months | Picks Due Month | PASS | DE VEGA & ESGUERRA | PALAHANG
UT_DUEDay_001 | New user tries to create an account within the mobile application. | Scroll gesture on designated number picker button | 1. User must scroll the number picker | 1. Scroll number picker | <Due Day> | User scroll number picker for due day | Days | Picks Due Day | PASS | DE VEGA & ESGUERRA | PALAHANG
UT_DUEYear_001 | New user tries to create an account within the mobile application. | Scroll gesture on designated number picker button | 1. User must scroll the number picker | 1. Scroll number picker | <Due Year> | User scroll number picker for due year | Years | Picks Due Year | PASS | DE VEGA & ESGUERRA | PALAHANG
UT_DUESelect_001 | New user tries to create an account within the mobile application. | Scroll gesture on designated number picker button | 1. User must scroll the number pickers | 1. Scroll number picker | <Due Month> | User scroll number picker for due date, Next Button will change color | Next Button enabled | Next button color changes and enabled | PASS | DE VEGA & ESGUERRA | PALAHANG
<Due Day>
<Due Year>
UT_DUEIdk_001 | New user tries to create an account within the mobile application. | Tap gesture on designated interactive button | 1. User must tap button | 1. Click "I don't know when is my due date" |  | User clicked on the button, next activity will appear | New activity will appear | Due date Calculator activity appears | PASS | DE VEGA & ESGUERRA | PALAHANG
UT_DUEButton_001 | New user tries to create an account within the mobile application. | Tap gesture on designated interactive button | 1. User must scroll the number pickers | 1. Scroll number pickers | <Due Month> | User clicked on select button, next activity will appear | New activity will appear | User Due date activity appears | PASS | DE VEGA & ESGUERRA | PALAHANG
|  |  |  | 2. Click "Next" | <Due Day>
<Due Year>
UT_DUECALCCal_001 | New user tries to create an account within the mobile application. | Tap gesture on calendar | 1. User must tap date on calendar view | 1. Pick month | <Last period date> | User select month and date on the calendar | Last Period Date | User Select Last Period Date | PASS | DE VEGA & ESGUERRA | PALAHANG
2. Pick date
UT_DUECALCSelect_001 | New user tries to create an account within the mobile application. | Scroll gesture on designated number picker button | 1. User must tap date on calendar view | 1. Pick month | <Last period date> | User select month and date on the calendar, Next Button will change color | Next Button enabled | Next button color changes and enabled | PASS | DE VEGA & ESGUERRA | PALAHANG
2. Pick date
UT_DUECALCButton_001 | New user tries to create an account within the mobile application. | Tap gesture on designated interactive button | 1. User must tap date on calendar view | 1. Pick month | <Last period date> | User clicked on next button, next activity will appear | New activity will appear | Profile Creation activity appears | PASS | DE VEGA & ESGUERRA | PALAHANG
2. Pick date
3. Click "Next"
UT_PROGRESSBar_001 | New user have just created an account within the mobile application. | Progress Bar for Profile Creation | 1. Test environment setup 2. Test data preparation 3. Test Availabity | 1. Create Account |  | When user created an account, progress bar should be displayed | Progress reached 100%, start the new activity | Official Welcome activity appears | PASS | DE VEGA & ESGUERRA | PALAHANG
2. Input Birthdate and mom experience
3. Input Due date or last period date
UT_WELCOMENext_001 | New user have just created an account within the mobile application. | Tap gesture on designated interactive button | 1. User must tap button | 1. Click "Next" |  | User clicked on the button, next activity will appear | New activity will appear | Homepage activity appears | PASS | DE VEGA & ESGUERRA | PALAHANG
UT_HOMENav_001 | Verify that if user clicks on any items from the navbar then user should be redirected on the destination page. | Tap gesture on designated interactive button | 1. User must tap button | 1. Click the menu button (hamburger) |  | User clicked on the button, NavigationView will appear | Navigataion Items | Navigataions appears | PASS | ESGUERRA | PALAHANG
UT_NAVProfile_001 | Verify that if user clicks on any items from the navbar then user should be redirected on the destination page. | Tap gesture on designated interactive text | 1. User must tap button | 1. Click the menu button (hamburger) | <Username> | User clicked on the button, Profile Fragment will appear | Username, Age and Due Date | User's infos appear | PASS | ESGUERRA | PALAHANG
|  |  |  | 2. Click "Profile" | <Age>
<Duedate>
UT_NAVAbout_001 | Verify that if user clicks on any items from the navbar then user should be redirected on the destination page. | Tap gesture on designated interactive text | 1. User must tap button | 1. Click the menu button (hamburger) |  | User clicked on the button, Profile Fragment will appear | Username, Age and Due Date | User's infos appears | PASS | ESGUERRA | PALAHANG
2. Click "About"
UT_NAVLogout_001 | Verify that if user clicks on any items from the navbar then user should be redirected on the destination page. | Tap gesture on designated interactive text | 1. User must tap button | 1. Click the menu button (hamburger) |  | User clicked on the button, user logout | Logout | Users logout, login page apperas | PASS | ESGUERRA | PALAHANG
2. Click "Logout"
UT_BUTTOMNAVHome_001 | Verify that if user clicks on any items from the navbar then user should be redirected on the destination page. | Tap gesture on designated interactive button | 1. User must tap button | 1. Click Home Icon |  | User clicked on the home button, user will be redirected to home fragment | Home page | Home Fragment view page appears | PASS | ESGUERRA | PALAHANG
UT_DASHBOARDDay_001 | Verify that if user clicks on any items from the navbar then user should be redirected on the destination page. | Tap gesture on designated interactive button | 1. User must tap button | 1. Click "Home" |  | User clicked on the home button, user's weeks and days of pregnancy and remaining days in pregnancy will show | Week N Day N Remaining Days N | User's number of weeks and days in pregnancy, and the remaining number of days for due date | PASS | DE VEGA & ESGUERRA | PALAHANG
UT_BUTTOMNAVCalendar_001 | Verify that if user clicks on any items from the navbar then user should be redirected on the destination page. | Tap gesture on designated interactive button | 1. User must tap button | 1. Click Calendar Icon |  | User clicked on the calendar button, user will be redirected to home fragment | Calendar page | Calendar Fragment view page appears | PASS | ESGUERRA | PALAHANG
UT_BUTTOMNAVHospital_001 | Verify that if user clicks on any items from the navbar then user should be redirected on the destination page. | Tap gesture on designated interactive button | 1. User must tap button | 1. Click Hospital Icon |  | User clicked on the hospital button, user will be redirected to hospitals near me fragment | Hospitals Near me page | Hospitals near me Fragment view page appears | PASS | ESGUERRA | PALAHANG
UT_BUTTOMNAVTips_001 | Verify that if user clicks on any items from the navbar then user should be redirected on the destination page. | Tap gesture on designated interactive button | 1. User must tap button | 1. Click Tips Icon |  | User clicked on the tips button, user will be redirected to tips and advice fragment | Tips and Advice page | Tips and Advice Fragment view page appears | PASS | ESGUERRA | PALAHANG

## Acceptance Testing
Project Name: |  | GO MOMMY!
Created by: |  | Sunshine Richmer Palahang
Date of creation: |  | 2023-06-13
Date of review:
TEST CASE ID | TEST SCENARIO | TEST CASE | PRE-CONDITION | TEST STEPS | TEST DATA | EXPECTED RESULT | POST CONDITION | ACTUAL RESULT | STATUS (PASS/FAIL) | Code by: | Tested by:
AT_SPLASH_001 | Verify that when User selects app Logo Splash screen is displayed with App Logo | Launch Application | 1. Test environment setup 2. Test data preparation 3. Test Availabity | 1. open application |  | When user selects app, splash screen of app logo should be displayed | Splash activity should remain for 3s only | App Logo displayed for no more than 3sec | PASS | DE VEGA & BAROTO | PALAHANG
2. show splash screen for 3sec
3. exit splash screen
AT_WELCOME_001 | Verify that when Splash screen end, welcome greetings will show | Launch Application | 1. Test environment setup 2. Test data preparation 3. Test Availabity | 1. open application |  | When splash screen is done displaying, welcome greetings should be displayed | ImageView should remain for 3s only | Welcome greetings for user displayed for no more than 3sec | PASS | DE VEGA & BAROTO | PALAHANG
2. show splash screen for 3sec
3. show welcome greetings
AT_T&C_001 | User agree on Terms and conditions | Tap gesture only on first checkbox | 1. User must tap checkbox | 1. Click first checkbox |  | Next button will not be shown and disabled | User cannot proceed | Next button is disabled | PASS | DE VEGA & BAROTO | PALAHANG
2. Click Next
AT_T&C_002 | User agree on Terms and conditions | Tap gesture only on second checkbox | 1. User must tap checkbox | 1. Click second checkbox |  | Next button will not be shown and disabled | User cannot proceed | Next button is disabled | PASS | DE VEGA & BAROTO | PALAHANG
2. Click Next
AT_T&C_003 | User agree on Terms and conditions | Tap gesture on all checkbox | 1. User must tap checkbox | 1. Click all checkbox |  | User clicked on next button, next activity will appear | New activity will appear | Next activity appears | PASS | DE VEGA & BAROTO | PALAHANG
2. Click Next
At_T&CDialog_001 | User agree on Terms and conditions | Tap gesture on designated interactive text | 1. User must tap Text | 1. Click "Privacy Policy and Terms of Use" |  | User clicked on interactive text, scrollable dialog box will appear | Dialog Box | Dialog Box appears | PASS | DE VEGA & ESGUERRA | PALAHANG
AT_T&CIunderstand_001 | User agree on Terms and conditions | Tap gesture on designated interactive text | 1. User must tap Text | 1. Click "Privacy Policy and Terms of Use" |  | User clicked on interactive text, dialog box will disappear | Dialog Box | Dialog Box disappears | PASS | DE VEGA & ESGUERRA | PALAHANG
2. Click "I understand"
AT_LOGIN_001 | Registered user tries to login within the mobile application. | Enter invalid email address and invalid Password | 1. Registered Email Address required. 2. Password must match from stored credentials. | 1. Enter E-mail Address | <Invalid Email> | A warning stating "The email address and password you entered do not match" shows. | Login unsuccessful | A warning stating "The email address and password you entered do not match" shows. | PASS | DE VEGA & ESGUERRA | PALAHANG
|  |  |  | 2. Enter Password | <Invalid Password>
3. Click "Login" button
AT_LOGIN_002 | Registered user tries to login within the mobile application. | Enter valid email address and invalid Password | 1. Registered Email Address required. 2. Password must match from stored credentials. | 1. Enter E-mail Address | <Valid Email> | A warning stating "Wrong Password" shows. | Login unsuccessful | A warning stating "Wrong Password" shows. | PASS | DE VEGA & ESGUERRA | PALAHANG
|  |  |  | 2. Enter Password | <Invalid Password>
3. Click "Login" button
AT_LOGIN_003 | Registered user tries to login within the mobile application. | Enter valid email address and valid Password | 1. Registered Email Address required. 2. Password must match from stored credentials. | 1. Enter E-mail Address | <Valid Email> | Next Activity will appear | Login successful | Next activity appears | PASS | DE VEGA & ESGUERRA | PALAHANG
|  |  |  | 2. Enter Password | <Valid Password>
3. Click "Login" button
AT_FORGOT_001 | Registered user tries to login within the mobile application. | Enter valid email address | 1. Email Address required | 1. Enter E-mail Address | <Valid Email>
2. Click "Reset" button
AT_CREATE_001 | New user tries to create an account within the mobile application. | Enter valid email address and valid Password | 1. Email Address required. 2. Password must be atleast 6 characters. 3. Confirm password must match password. | 1. Enter E-mail Address | <Valid Email> | Next Activity will appear | Create Account successful | Next activity appears | PASS | DE VEGA & ESGUERRA | PALAHANG
|  |  |  | 2. Enter Password and Confirm Password | <Valid Password>
|  |  |  | 3. Click "Create Account" button | <Password match>
AT_CREATE_002 | New user tries to create an account within the mobile application. | Enter invalid email address and valid Password | 1. Email Address required. 2. Password must be atleast 6 characters. 3. Confirm password must match password. | 1. Enter E-mail Address | <Invalid Email> | A warning stating "The email address is badly formatted" shows. | Create Account unsuccessful | A warning stating "The email address is badly formatted" shows. | PASS | DE VEGA & ESGUERRA | PALAHANG
|  |  |  | 2. Enter Password and Confirm Password | <Valid Password>
|  |  |  | 3. Click "Create Account" button | <Password match>
AT_CREATE_003 | New user tries to create an account within the mobile application. | Enter registered email address and valid Password | 1. Email Address required. 2. Password must be atleast 6 characters. 3. Confirm password must match password. | 1. Enter E-mail Address | <Invalid Email> | A warning stating "The email address is already in use by another account" shows. | Create Account unsuccessful | A warning stating "The email address is already in use by another account" shows. | PASS | DE VEGA & ESGUERRA | PALAHANG
|  |  |  | 2. Enter Password and Confirm Password | <Valid Password>
|  |  |  | 3. Click "Create Account" button | <Password match>
AT_CREATE_004 | New user tries to create an account within the mobile application. | Enter registered email address and invalid Password | 1. Email Address required. 2. Password must be atleast 6 characters. 3. Confirm password must match password. | 1. Enter E-mail Address | <Invalid Email> | A warning stating "The given password is invalid. [Password should be at least 6 characters]" shows. | Create Account unsuccessful | A warning stating "The given password is invalid. [Password should be at least 6 characters]" shows. | PASS | DE VEGA & ESGUERRA | PALAHANG
|  |  |  | 2. Enter Password and Confirm Password | <Invalid Password>
|  |  |  | 3. Click "Create Account" button | <Password match>
AT_CREATE_005 | New user tries to create an account within the mobile application. | Enter registered email address and invalid Password | 1. Email Address required. 2. Password must be atleast 6 characters. 3. Confirm password must match password. | 1. Enter E-mail Address | <Invalid Email> | A warning stating "Password does not match" shows. Create account but disabled. | Create Account unsuccessful | A warning stating "Password does not match" shows. Create account but disabled. | PASS | DE VEGA & ESGUERRA | PALAHANG
|  |  |  | 2. Enter Password and Confirm Password | <Invalid Password>
|  |  |  | 3. Click "Create Account" button | <Password does not match>
AT_CREATE_006 | New user tries to create an account within the mobile application. | Enter valid email address and invalid Password | 1. Email Address required. 2. Password must be atleast 6 characters. 3. Confirm password must match password. | 1. Enter E-mail Address | <Valid Email> | A warning stating "The given password is invalid. [Password should be at least 6 characters]" shows. | Create Account unsuccessful | A warning stating "The given password is invalid. [Password should be at least 6 characters]" shows. | PASS | DE VEGA & ESGUERRA | PALAHANG
|  |  |  | 2. Enter Password and Confirm Password | <Invalid Password>
|  |  |  | 3. Click "Create Account" button | <Password match>
AT_CREATE_007 | New user tries to create an account within the mobile application. | Enter valid email address, invalid Password but confirm password does not match | 1. Email Address required. 2. Password must be atleast 6 characters. 3. Confirm password must match password. | 1. Enter E-mail Address | <Valid Email> | A warning stating "Password does not match" shows. Create account but disabled. | Create Account unsuccessful | A warning stating "Password does not match" shows. Create account but disabled. | PASS | DE VEGA & ESGUERRA | PALAHANG
|  |  |  | 2. Enter Password and Confirm Password | <Invalid Password>
|  |  |  | 3. Click "Create Account" button | <Password does not match>
AT_CREATE_008 | New user tries to create an account within the mobile application. | Enter valid email address, valid Password but confirm password does not match | 1. Email Address required. 2. Password must be atleast 6 characters. 3. Confirm password must match password. | 1. Enter E-mail Address | <Valid Email> | A warning stating "Password does not match" shows. Create account but disabled. | Create Account unsuccessful | A warning stating "Password does not match" shows. Create account but disabled. | PASS | DE VEGA & ESGUERRA | PALAHANG
|  |  |  | 2. Enter Password and Confirm Password | <Valid Password>
|  |  |  | 3. Click "Create Account" button | <Password does not match>
AT_FORGOT_001 | Registered user tries to login within the mobile application. | Tap gesture on designated interactive text | 1. Registered Email Address Required | 1. Click "Forgot Password?" |  | User clicked on forgot password interactive text, forgot password activity will appear | New activity will appear | "Forgot Password?" interactive text is unable to click | FAIL | BAROTO & ESGUERRA | PALAHANG
AT_GOOGLE_001 | New user tries to create an account within the mobile application. | Tap gesture on designated interactive button | 1. Google Account required. | 1. Click "Create with Google " |  | User clicked on create with google button, google account/s will appear | Google Account | "Create with Google" button is unable to click | FAIL | BAROTO & ESGUERRA | PALAHANG
AT_MOMEXP_001 | New user tries to create an account within the mobile application. | Tap gesture on designated interactive button | 1. User must tap one button | 1. Click "Yes, I am a first time mom" |  | User clicked on no button, next activity will appear | New activity will appear | Birthyear picker activity appears | PASS | DE VEGA & ESGUERRA | PALAHANG
AT_MOMEXP_002 | New user tries to create an account within the mobile application. | Tap gesture on designated interactive button | 1. User must tap one button | 1. Click "No, I have had children before" |  | User clicked on no button, next activity will appear | New activity will appear | Birthyear picker activity appears | PASS | DE VEGA & ESGUERRA | PALAHANG
AT_BIRTHYEAR_001 | New user tries to create an account within the mobile application. | Tap gesture on designated interactive button | 1. User must scroll the number picker | 1. Scroll number picker | <Birthyear> | User clicked on select button, next activity will appear. User birthyear stored in fire base | Data stored successfully | User Due date activity appears. User age stored | PASS | DE VEGA & ESGUERRA | PALAHANG
2. Click "Select"
AT_DUE_001 | New user tries to create an account within the mobile application. | Tap gesture on designated interactive button | 1. User must scroll the number pickers | 1. Scroll number pickers | <Due Month> | User clicked on select button, next activity will appear. User Due date stored in firebase | Data stored successfully | User Due date activity appears. User due date stored | PASS | DE VEGA & ESGUERRA | PALAHANG
|  |  |  | 2. Click "Next" | <Due Day>
<Due Year>
AT_LASTPERIOD_001 | New user tries to create an account within the mobile application. | Tap gesture on designated interactive button | 1. User must tap date on calendar view | 1. Pick month | <Last period date> | User clicked on next button, next activity will appear. user last period stored, calculate estimated due date | Data stored successfully | Profile Creation activity appears. User estimated due date stored | PASS | DE VEGA & ESGUERRA | PALAHANG
2. Pick date
3. Click "Next"
AT_HOME_001 | Verify that if user clicks on any items from the navbar then user should be redirected on the destination page. | Tap gesture on designated interactive button | 1. User must tap button | 1. Click the menu button (hamburger) |  | User clicked on the button, NavigationView will appear | Navigataion Items | Navigataions appears | PASS | ESGUERRA | PALAHANG
AT_PROFILE_001 | Verify that if user clicks on any items from the navbar then user should be redirected on the destination page. | Tap gesture on designated interactive text | 1. User must tap button | 1. Click the menu button (hamburger) | <Username> | User clicked on the button, Profile Fragment will appear | Username, Age and Due Date | User's infos appear | PASS | ESGUERRA | PALAHANG
|  |  |  | 2. Click "Profile" | <Age>
<Duedate>
AT_ABOUT_001 | Verify that if user clicks on any items from the navbar then user should be redirected on the destination page. | Tap gesture on designated interactive text | 1. User must tap button | 1. Click the menu button (hamburger) |  | User clicked on the button, Profile Fragment will appear | Username, Age and Due Date | User's infos appears | PASS | ESGUERRA | PALAHANG
2. Click "About"
AT_LOGOUT_001 | Verify that if user clicks on any items from the navbar then user should be redirected on the destination page. | Tap gesture on designated interactive text | 1. User must tap button | 1. Click the menu button (hamburger) |  | User clicked on the button, user logout | Logout | Users logout, login page apperas | PASS | ESGUERRA | PALAHANG
2. Click "Logout"
AT_DASHBOARDIcon_001 | Verify that if user clicks on any items from the navbar then user should be redirected on the destination page. | Tap gesture on designated interactive button | 1. User must tap button | 1. Click Home Icon |  | User clicked on the home button, user will be redirected to home fragment | Home page | Home Fragment view page appears | PASS | ESGUERRA | PALAHANG
AT_CALENDARIcon_001 | Verify that if user clicks on any items from the navbar then user should be redirected on the destination page. | Tap gesture on designated interactive button | 1. User must tap button | 1. Click Calendar Icon |  | User clicked on the calendar button, user will be redirected to home fragment | Calendar page | Calendar Fragment view page appears | PASS | ESGUERRA | PALAHANG
AT_HOSPITALIcon_001 | Verify that if user clicks on any items from the navbar then user should be redirected on the destination page. | Tap gesture on designated interactive button | 1. User must tap button | 1. Click Hospital Icon |  | User clicked on the hospital button, user will be redirected to hospitals near me fragment | Hospitals Near me page | Hospitals near me Fragment view page appears | PASS | ESGUERRA | PALAHANG
AT_TIPSIcon_001 | Verify that if user clicks on any items from the navbar then user should be redirected on the destination page. | Tap gesture on designated interactive button | 1. User must tap button | 1. Click Tips Icon |  | User clicked on the tips button, user will be redirected to tips and advice fragment | Tips and Advice page | Tips and Advice Fragment view page appears | PASS | ESGUERRA | PALAHANG

## Regression Testing
Project Name: |  | GO MOMMY!
Created by: |  | Sunshine Richmer Palahang
Date of creation: |  | 2023-06-13
Date of review:
TEST CASE ID | TEST SCENARIO | TEST CASE | PRE-CONDITION | TEST STEPS | TEST DATA | EXPECTED RESULT | POST CONDITION | ACTUAL RESULT | STATUS (PASS/FAIL) | Code by: | Tested by:
RT_SPLASH_001 | Verify that when User selects app Logo Splash screen is displayed with App Logo | Display activity for 3secs | 1. Test environment setup 2. Test data preparation 3. Test Availabity | 1. open application |  | When user selects app, splash screen of app logo should be displayed | Splash activity should remain for 3s | App Logo displayed for no more than 3sec | PASS | DE VEGA & BAROTO | PALAHANG
2. show splash screen for 3sec
3. exit splash screen
RT_WELCOME_001 | Verify that when Splash screen end, welcome greetings will show | Launch Application | 1. Test environment setup 2. Test data preparation 3. Test Availabity | 1. open application |  | When splash screen is done displaying, welcome greetings should be displayed | ImageView should remain for 3s only | Welcome greetings for user displayed for no more than 3sec | PASS | DE VEGA & BAROTO | PALAHANG
2. show splash screen for 3sec
3. show welcome greetings
RT_T&C_001 | User agree on Terms and conditions | Tap gesture on all checkbox | 1. User must tap checkbox | 1. Click all checkbox |  | User clicked on next button, next activity will appear | New activity will appear | Next activity appears | PASS | DE VEGA & BAROTO | PALAHANG
2. Click Next
RT_LOGIN_001 | Registered user tries to login within the mobile application. | Enter valid email address and valid Password | 1. Registered Email Address required. 2. Password must match from stored credentials. | 1. Enter E-mail Address | <Valid Email> | Next Activity will appear | Login successful | Next activity appears | PASS | DE VEGA & ESGUERRA | PALAHANG
|  |  |  | 2. Enter Password | <Valid Password>
3. Click "Login" button
RT_HOME_001 | Registered user tries to login within the mobile application. | Enter valid email address and valid Password | 1. Registered Email Address required. 2. Password must match from stored credentials. | 1. Enter E-mail Address | <Valid Email> | Next Activity will appear | Login successful | App exits | FAIL | DE VEGA & ESGUERRA | PALAHANG
|  |  |  | 2. Enter Password | <Valid Password>
3. Click "Login" button
RT_CREATE_001 | Registered user tries to create an account within the mobile application. | Enter valid email address and valid Password | 1. Email Address required. 2. Password must be atleast 6 characters. 3. Confirm password must match password. | 1. Enter E-mail Address | <Valid Email> | Next Activity will appear | Create Account successful | Next activity appears | PASS | DE VEGA & ESGUERRA | PALAHANG
|  |  |  | 2. Enter Password and Confirm Password | <Valid Password>
|  |  |  | 3. Click "Create Account" button | <Password match>
RT_FORGOT_001 | Registered user tries to login within the mobile application. | Tap gesture on designated interactive text | 1. Registered Email Address Required | 1. Click "Forgot Password?" |  | User clicked on forgot password interactive text, forgot password activity will appear | New activity will appear | "Forgot Password?" interactive text is unable to click | FAIL | BAROTO & ESGUERRA | PALAHANG
RT_GOOGLE_001 | New user tries to create an account within the mobile application. | Tap gesture on designated interactive button | 1. Google Account required. | 1. Click "Create with Google " |  | User clicked on create with google button, google account/s will appear | Google Account | "Create with Google" button is unable to click | FAIL | BAROTO & ESGUERRA | PALAHANG
RT_MOMEXP_001 | New user tries to create an account within the mobile application. | Tap gesture on designated interactive button | 1. User must tap one button | 1. Click "Yes, I am a first time mom" or "No, I have had children before" |  | User clicked on no button, next activity will appear | New activity will appear | Birthyear picker activity appears | PASS | DE VEGA & ESGUERRA | PALAHANG
RT_BIRTHYEAR_001 | New user tries to create an account within the mobile application. | Tap gesture on designated interactive button | 1. User must scroll the number picker | 1. Scroll number picker | <Birthyear> | User clicked on select button, next activity will appear. User birthyear stored in fire base | Data stored successfully | User Due date activity appears. User age stored | PASS | DE VEGA & ESGUERRA | PALAHANG
2. Click "Select"
RT_DUE_001 | New user tries to create an account within the mobile application. | Tap gesture on designated interactive button | 1. User must scroll the number pickers | 1. Scroll number pickers | <Due Month> | User clicked on select button, next activity will appear. User Due date stored in firebase | Data stored successfully | User Due date activity appears. User due date stored | PASS | DE VEGA & ESGUERRA | PALAHANG
|  |  |  | 2. Click "Next" | <Due Day>
<Due Year>
RT_LASTPERIOD_001 | New user tries to create an account within the mobile application. | Tap gesture on designated interactive button | 1. User must tap date on calendar view | 1. Pick month | <Last period date> | User clicked on next button, next activity will appear. user last period stored, calculate estimated due date | Data stored successfully | Profile Creation activity appears. User estimated due date stored | PASS | DE VEGA & ESGUERRA | PALAHANG
2. Pick date
3. Click "Next"
RT_HOME_001 | Verify that if user clicks on any items from the navbar then user should be redirected on the destination page. | Tap gesture on designated interactive button | 1. User must tap button | 1. Click the menu button (hamburger) |  | User clicked on the button, NavigationView will appear | Navigataion Items | Navigataions appears | PASS | ESGUERRA | PALAHANG
RT_PROFILE_001 | Verify that if user clicks on any items from the navbar then user should be redirected on the destination page. | Tap gesture on designated interactive text | 1. User must tap button | 1. Click the menu button (hamburger) | <Username> | User clicked on the button, Profile Fragment will appear | Username, Age and Due Date | User's infos appear | PASS | ESGUERRA | PALAHANG
|  |  |  | 2. Click "Profile" | <Age>
<Duedate>
RT_ABOUT_001 | Verify that if user clicks on any items from the navbar then user should be redirected on the destination page. | Tap gesture on designated interactive text | 1. User must tap button | 1. Click the menu button (hamburger) |  | User clicked on the button, Profile Fragment will appear | Username, Age and Due Date | User's infos appears | PASS | ESGUERRA | PALAHANG
2. Click "About"
RT_LOGOUT_001 | Verify that if user clicks on any items from the navbar then user should be redirected on the destination page. | Tap gesture on designated interactive text | 1. User must tap button | 1. Click the menu button (hamburger) |  | User clicked on the button, user logout | Logout | Users logout, login page apperas | PASS | ESGUERRA | PALAHANG
2. Click "Logout"
RT_DASHBOARD_001 | Verify that if user clicks on any items from the navbar then user should be redirected on the destination page. | Tap gesture on designated interactive button | 1. User must tap button | 1. Click Home Icon |  | User clicked on the home button, user will be redirected to home fragment | Home page | Home Fragment view page appears | PASS | ESGUERRA | PALAHANG
RT_CALENDAR_001 | Verify that if user clicks on any items from the navbar then user should be redirected on the destination page. | Tap gesture on designated interactive button | 1. User must tap button | 1. Click Calendar Icon |  | User clicked on the calendar button, user will be redirected to home fragment | Calendar page | Calendar Fragment view page appears | PASS | ESGUERRA | PALAHANG
RT_HOSPITAL_001 | Verify that if user clicks on any items from the navbar then user should be redirected on the destination page. | Tap gesture on designated interactive button | 1. User must tap button | 1. Click Hospital Icon |  | User clicked on the hospital button, user will be redirected to hospitals near me fragment | Hospitals Near me page | Hospitals near me Fragment view page appears | PASS | ESGUERRA | PALAHANG
RT_TIPS_001 | Verify that if user clicks on any items from the navbar then user should be redirected on the destination page. | Tap gesture on designated interactive button | 1. User must tap button | 1. Click Tips Icon |  | User clicked on the tips button, user will be redirected to tips and advice fragment | Tips and Advice page | Tips and Advice Fragment view page appears | PASS | ESGUERRA | PALAHANG